VERIFY-DR

Project Assessment and Revised Plan

Evidence-verified diabetic retinopathy grading with disagreement-gated referral

MSc thesis — assessment of the EyePACS-centred blueprint, revised design, and experiment programme

Prepared for supervisor review

13 September 2026

# Contents

(Right-click → Update Field in Word to populate page numbers.)

# 1. Executive summary

The original blueprint describes an ambitious auditable diabetic-retinopathy (DR) grading system built around EyePACS, with an independent lesion-evidence pathway, an ICDR rule reasoner, counterfactual verification, calibration, out-of-distribution screening and selective triage.

The engineering discipline in that document is unusually good — a locked external dataset, an explicit manifest contract, multi-seed evaluation and an intent to group splits by patient are better than much of the published DR literature. The problems are in scope and in scientific framing, not in care.

| Question | Assessment |
| --- | --- |
| Viable as an MSc thesis? | Yes, but over-scoped by roughly 3× and centred on a component the blueprint itself admits it cannot train. |
| New or better than existing papers? | Not as written. Every component is individually published, and the specified recipe will produce accuracy below the 2015 Kaggle leaderboard. One narrow axis is genuinely novel. |
| Works cross-dataset? | Yes — this is the strongest part of the design. But calibration, not accuracy, is what will break. |

The single most important change Stop competing on grading accuracy. Compete on knowing when the grade can be trusted. The revised thesis asks one question: can disagreement between an image-level grader and an independently-supervised lesion-evidence pathway decide which automated gradings to trust — better than the model's own confidence, and does that survive a change of dataset?

# 2. Assessment of the original blueprint

## 2.1 The headline contribution is unimplementable as specified

The blueprint's pitch is an independent evidence pathway feeding an ICDR reasoner with counterfactual verification. Section 11 then concedes that the datasets carry no lesion masks, so the evidence model is untrained, the reasoner has no facts, and the triage policy defers everything. An examiner will ask what was actually evaluated, and the honest answer is “an ordinal EfficientNet-B0”.

Two details make this worse than the blueprint suggests.

- The eight lesion channels do not exist in any Kaggle-available dataset. DDR — already loaded by the blueprint for grading — ships a pixel-annotated segmentation subset of roughly 757 images with four lesion types. IDRiD adds 81 more, plus optic-disc and fovea coordinates. The blueprint discards exactly the annotations its architecture requires.

- The ICDR rules cannot be evaluated from masks alone. The 4-2-1 rule needs haemorrhage counts per quadrant, venous beading in at least two quadrants, and IRMA in at least one. Segmentation gives pixels, not quadrants; quadrants need optic-disc and fovea localisation to establish a coordinate frame. Venous beading, IRMA and neovascularisation have no pixel labels anywhere on Kaggle.

Both are fixable, and the fixes are in Section 4.

## 2.2 Two flaws that would inflate or invalidate the numbers

Patient leakage. The blueprint's “conservative image-stem proxy” makes every image its own patient, so a patient's left and right eyes land on opposite sides of the split. Both eyes of one diabetic are strongly correlated; this measurably inflates QWK, and DR reviewers check for it. EyePACS filenames are <patient>_left / <patient>_right — real patient identifiers are available for free.

Unspecified input resolution. Grade 1 is microaneurysms only. A microaneurysm is roughly 10–20 pixels at full resolution and does not survive aggressive downsampling. The blueprint pins backbone, sampler, focal gamma and epoch count, but never pins image size — which is the single largest lever on QWK in this task.

Secondary: no ensembling and no two-eye fusion. Every strong EyePACS result exploits inter-eye correlation. Skipping it while training eight epochs of EfficientNet-B0 makes an internal QWK around 0.75–0.82 the likely outcome, against roughly 0.85 for the 2015 competition winner.

## 2.3 The compute plan does not fit on Kaggle

Kaggle provides 30 GPU-hours per week with a 12-hour session cap. Full EyePACS at 512 px for eight epochs on a T4 is roughly 3–5 hours per run, with JPEG decode of large fundus images — not the GPU — as the bottleneck. The blueprint's schedule of four variants × three suites × multiple configurations × three seeds runs into the low hundreds of GPU-hours per variant: approximately a year of wall-clock time.

The fix that makes the project feasible Pre-resize the corpus to 512 px once and publish it as a private Kaggle dataset. Epoch time drops from 25–40 minutes to 7–9 minutes; a training run drops from about 4 hours to about 1.5. Combined with a trimmed experiment grid, total project cost falls to roughly 100 GPU-hours — three to four weeks of quota.

## 2.4 Is any of it new?

Component by component: ordinal thresholds (CORAL/CORN), temperature scaling (Guo 2017), uncertainty-based referral in DR specifically (Leibig 2017), lesion-aware grading (Wei 2020; Sun 2021), counterfactual explanation for DR (Boreiko 2022) and embedding-distance OOD detection are all published, most of them in DR. Integration alone is an engineering contribution, not a research one.

Where genuine novelty is available:

Deferral triggered by grade-versus-evidence disagreement, not by confidence Standard selective prediction defers when the classifier is unsure. This design can defer when the classifier is confident but an independently-supervised evidence pathway contradicts it — and the counterfactual test becomes a faithfulness check rather than an explanation: if the lesions the reasoner cited are removed and the grade does not move, the stated reason was not the operative one. That is testable, falsifiable, and survives the reduced four-channel lesion set.

# 3. The revised research question

Can disagreement between an image-level DR grader and an independently-supervised lesion-evidence pathway be used to decide which automated gradings to trust — and does that decision rule transfer across datasets better than gating on the model's own confidence?

## 3.1 Hypotheses, stated before any experiment runs

|  | Hypothesis | Decided by | Falsified if |
| --- | --- | --- | --- |
| H1 | Disagreement-gating dominates confidence-gating on the coverage–accuracy curve | F1 | Confidence-gating matches or beats it at equal coverage |
| H2 | Prior-shift correction restores external calibration that temperature scaling alone loses | D3 | External ECE unchanged after correction |
| H3 | Adding DDR to training improves external transfer | B7 | External QWK unchanged or worse |
| H1′ | The H1 ranking survives dataset shift — the one that matters | F2 | Disagreement wins internally but not externally |

Why this works as a thesis question All four hypotheses may come out negative and the thesis still stands, provided they were pre-registered. A negative result on selective prediction in DR is worth more to the field than a fudged positive, because almost nobody publishes them. What would not be a thesis is discovering the outcome first and writing the question around it. That is what the Phase 5 freeze prevents.

## 3.2 Contributions claimed

- Primary — deferral gated on grade-versus-evidence disagreement rather than model confidence, evaluated under dataset shift.

- Secondary — prior-shift-corrected calibration across DR datasets with differing grade prevalence.

- Tertiary — a reasoner that declares its own unobservable findings and abstains upward rather than emitting a confident grade on evidence it does not have.

## 3.3 Explicitly not claimed

- State-of-the-art grading accuracy. A single EfficientNet-B0 at 512 px with no heavy ensemble will land below the best published EyePACS numbers, and the abstract says so. Framing this as an accuracy contribution would lose the argument in the viva.

- Clinical validity. Research software; deployment would require prospective validation and expert oversight.

- Full ICDR compliance. Venous beading, IRMA and neovascularisation are unobservable with Kaggle data, and single macula-centred fields cannot support true four-quadrant assessment.

# 4. Changes from the original blueprint

Every concept in the blueprint, its verdict, and what replaces it. Grouped by area.

| Area | Current concept | Verdict | Replacement |
| --- | --- | --- | --- |
| Data | EyePACS as primary development source | Keep | Unchanged — the right call |
| Data | Custom 80 / val / calibration / test split as headline | Change | Official EyePACS competition split (35,126 / 53,576, already patient-disjoint); carve val and calibration out of train only |
| Data | patient_id from image-stem proxy | Change | Parse ^(\d+)_(left¦right)$ for real patient IDs; fixes eye-pair leakage |
| Data | Five variants: 500 / 1000 / 2000 / full / merged | Change | Three: eyepacs_full, eyepacs_balanced_1000, eyepacs_ddr_full |
| Data | Balanced variants as headline results | Change | Demoted to a sampling ablation; all test sets keep natural prevalence |
| Data | DDR used for grading merge only | Change | Dual role — grading merge and lesion-mask source |
| Data | DDR grade 5 (ungradable) unhandled | Add | Becomes supervision for the quality / REACQUIRE head |
| Data | APTOS as the only external set | Change | Two locked externals: APTOS and Messidor-2 (adjudicated grades) |
| Data | IDRiD not used | Add | Lesion masks, optic-disc and fovea coordinates, and a 516-image grading set |
| Data | Eight-channel mask source (FGADR-class) | Remove | Not obtainable on Kaggle — requires a signed agreement. Forces the four-channel design |
| Data | Raw JPEG reads from /kaggle/input | Change | One-off 512 px pre-resize into a private Kaggle dataset. The compute unlock |
| Model | EfficientNet-B0 / ResNet50 with four monotonic ordinal thresholds | Keep | Unchanged |
| Model | Image size unspecified | Add | Fixed at 512 px; 384 / 512 / 768 is experiment B1 |
| Model | Single-image prediction | Add | Eye-pair fusion (concatenate left and right features) — cheap, historically a large QWK gain |
| Model | Eight lesion channels | Change | Four: microaneurysm, haemorrhage, hard exudate, soft exudate |
| Model | Evidence path untrained (no masks) | Change | ResNet18-UNet trained on DDR-seg and IDRiD-seg; reported with Dice and IoU |
| Model | No optic-disc / fovea localiser | Add | Coordinate regressor trained on IDRiD — enables quadrant geometry |
| Reasoner | Full ICDR including 4-2-1, venous beading, IRMA, neovascularisation | Change | Partial ICDR: the haemorrhage arm of 4-2-1 via optic-disc/fovea quadrants, plus MA presence |
| Reasoner | Emits a confident evidence grade | Change | Emits grade plus an explicit unobservable set; abstains upward (“cannot exclude severe NPDR”) |
| Reasoner | Counterfactual “lesion-token test” | Promote | Lesion-region inpainting counterfactual as a faithfulness test — the headline mechanism |
| Triage | Gate on confidence plus OOD z-score | Change | Gate on grade-versus-evidence disagreement; confidence-only and OOD-only become baselines |
| Triage | OOD z-score as a contribution | Change | Demoted to a comparator arm — keep the code, drop the novelty claim |
| Calibration | Temperature scaling on the internal split | Change | Plus prior-shift correction (Saerens–Decock EM / logit adjustment) for externals — contribution #2 |
| Evaluation | QWK on a custom split | Change | Report on the official EyePACS test split — directly comparable to the 0.8496 leaderboard; state the protocol explicitly |
| Evaluation | Bootstrap CI only | Add | Paired seed-level tests plus coverage–accuracy AUC for the selective claim |
| Protocol | “APTOS never used for tuning” | Keep + harden | Pre-register the frozen recipe (commit hash and config) before the first external run |
| Framing | “Combines ordinal + evidence + reasoner + CF + calibration + OOD + triage” | Change | One question: does disagreement-gating beat confidence-gating, and does it transfer? |
| Scope | Verification suite “only when masks are available” | Change | Now runnable — it is the thesis |
| Compute | Four variants × three suites × three seeds × eight epochs | Change | Staged: one seed to explore, three seeds only on the frozen recipe (~100 GPU-h total) |

The one genuinely new idea in that table The reasoner will know things it cannot see. Venous beading, IRMA and neovascularisation have no pixel labels on Kaggle, and single macula-centred fields cannot support proper four-quadrant assessment. Rather than hiding that, the reasoner emits its own blind spots and abstains upward. A system that says “I see 12 haemorrhages across 3 quadrants and no exudate, but I cannot observe IRMA, so I cannot exclude severe NPDR — defer” is more clinically honest than one that guesses. The dataset limitation becomes the contribution.

# 5. Dataset roster — Kaggle only

Every source is Kaggle-hosted, so the whole project runs in a Kaggle notebook.

| Dataset | Kaggle slug | Role | Locked? |
| --- | --- | --- | --- |
| EyePACS | tantai31124/eyepacs-original | Primary development | No |
| DDR | mariaherrerot/ddrdataset | Merged dev + lesion masks + ungradable class | No |
| IDRiD | mariaherrerot/idrid-dataset (or mirror) | Lesion masks + OD/fovea coords + grading | No |
| APTOS 2019 | aptos2019-blindness-detection | External test #1 | YES |
| Messidor-2 images | mariaherrerot/messidor2preprocess | External test #2 | YES |
| Messidor-2 grades | google-brain/messidor2-dr-grades | Adjudicated labels — join by image ID | YES |

## 5.1 Two verification questions to answer before anything else

- Does the DDR mirror actually ship lesion_segmentation/, not only DR_grading/? If it does not, the evidence pathway has no training data and there is no version of this thesis without it.

- What preprocessing has messidor2preprocess already applied? If the images are already contrast-normalised, the measured “domain gap” is partly an artefact and must be matched or reported.

## 5.2 The prevalence shift is the point

| Dataset | Grade 0 | Grade 1 | Grade 2 | Grade 3 | Grade 4 | n |
| --- | --- | --- | --- | --- | --- | --- |
| EyePACS (train) | 73.5% | 7.0% | 15.1% | 2.5% | 2.0% | 35,126 |
| APTOS 2019 (train) | 49.3% | 10.1% | 27.3% | 5.3% | 8.1% | 3,662 |

Grade-0 prevalence moves from roughly 73% to 49% between the two. That is why a temperature fitted on EyePACS will not transfer to APTOS (experiment D2), and why prior-shift correction is a real contribution rather than a technicality (D3). Positive predictive value depends entirely on getting this right.

# 6. Experiment programme

Twenty-six experiments. Everything before Stage F exists to make Stage F trustworthy. Model selection happens only in B1–B5; external data is touched exactly once, after the freeze.

## Stage A — Infrastructure (no claims)

| ID | Question | Decided by |
| --- | --- | --- |
| A0 | Did the 512 px cache preserve the data? | Counts reconcile per grade; crop failures < 0.5%; 100-crop visual audit |
| A1 | Does the pipeline run end to end? | Smoke test completes; one-epoch pilot gives non-trivial QWK |

## Stage B — Grading pathway (selection; validation only)

| ID | Question | Varies | Decided by |
| --- | --- | --- | --- |
| B1 | What resolution is needed? | 384 / 512 / 768 px | Val QWK and grade-1 recall |
| B2 | Which encoder? | EfficientNet-B0 / ResNet50 | Val QWK per GPU-hour |
| B3 | Which head? | CE / ordinal / focal-ordinal | Val QWK and MAE |
| B4 | Which sampler? | Natural / stratified / balanced | Val QWK at natural prevalence |
| B5 | Does eye-pair fusion help? | Single vs left+right fusion | Val QWK, paired across seeds |
| B6 | Does balancing the dataset help? (ablation) | full vs balanced_1000 | QWK on natural-prevalence test |
| B7 | Does DDR improve transfer? (H3) | full vs ddr_full | External QWK — single unblinding |

B1 warning Judge B1 on grade-1 recall, not overall QWK. Grade 1 is microaneurysms only and an MA is 10–20 pixels. A model that silently skips grade 1 can still post a respectable QWK, and the resulting thesis would rest on a hollow number.

## Stage C — Evidence pathway

| ID | Question | Decided by |
| --- | --- | --- |
| C1 | Can we locate disc and fovea well enough for quadrants? | Euclidean error on IDRiD test in disc diameters (target < 0.5 DD) |
| C2 | How well do the four lesion channels segment? | Per-lesion Dice and IoU |
| C3 | Does the segmenter itself transfer? | Dice drop, DDR→IDRiD and reverse |
| C4 | How informative is evidence alone? | QWK of evidence-grade against the true label |

C4 is load-bearing The evidence pathway must be informative but weaker than the grader. If it matches the grader, the grader is redundant; if it is noise, disagreement means nothing. Report this number honestly whichever way it lands — the thesis needs it interpretable, not good.

## Stage D — Calibration (H2)

| ID | Question | Decided by |
| --- | --- | --- |
| D1 | Is the model calibrated internally? | ECE, NLL, Brier — uncalibrated vs temperature scaling |
| D2 | Does internal temperature transfer? | External ECE on APTOS and Messidor-2 — expected to fail |
| D3 | Does prior-shift correction fix it? | External ECE; Saerens–Decock EM against an oracle-prior upper bound |
| D4 | How much unlabelled target data does EM need? | ECE versus n = 50 / 200 / 500 / all |

D2 failing is the finding, not a bug. The EM step in D3 reads unlabelled target images only — no target labels — so it does not break the external lock. This must be stated in the methods so no reviewer mistakes it for leakage.

## Stage E — Verification and faithfulness

| ID | Question | Decided by |
| --- | --- | --- |
| E1 | Does removing cited lesions change the grade? | Δgrade distribution after inpainting predicted lesion regions |
| E2 | Is that shift lesion-specific? | Δ(lesion) versus Δ(random regions of equal area) |
| E3 | Does faithfulness hold at every severity? | Δgrade stratified by true grade — grade 1 is the hard case |

E2 is mandatory Without the random-region control, E1 measures that the model reacts to inpainting — not that it uses the lesions. This control is the difference between a faithfulness test and a demonstration of nothing. Every reviewer will ask for it.

## Stage F — Selective triage (H1, the headline)

| ID | Question | Decided by |
| --- | --- | --- |
| F1 | Best gating signal, internally? | Coverage–accuracy AUC; accuracy at 80% and 90% coverage, across five arms |
| F2 | Does the ranking survive dataset shift? | Same metrics on APTOS and Messidor-2 |
| F3 | What does it mean clinically? | rDR sensitivity and specificity at fixed coverage |
| F4 | Which form of the signal works? | Binary / magnitude / magnitude plus unobservable set |
| F5 | Where do cases actually land? | Fraction and accuracy per action bucket |

The five arms are: no gate, confidence only, OOD-z only, disagreement only, and combined. Confidence-only is the Leibig-style baseline this project exists to test against.

F2 is the thesis A signal that only wins in-domain is a curiosity. One that holds up under dataset shift is a contribution.

## Stages G and H — Error analysis and benchmark

| ID | Question |
| --- | --- |
| G1 | Which errors does disagreement catch that confidence misses, and vice versa? Set overlap plus real examples — this produces figure 1 |
| G2 | Does the quality head flag genuinely ungradable images? Held-out DDR grade-5 as ground truth |
| G3 | Failure taxonomy: where does the reasoner contradict a correct grade? |
| H1 | QWK on the official EyePACS test split, reported beside the 0.8496 leaderboard reference — the one directly comparable number |

# 7. What the final output looks like

## 7.1 Per image, at inference

Every image produces a structured decision record, not just a grade:

{

"image_id": "16_left.jpeg",  "patient_id": "EyePACS::16",

"quality":       { "score": 0.87, "gradable": true },

"grade_pathway": { "predicted_grade": 2,

"probabilities": [0.03, 0.11, 0.68, 0.15, 0.03],

"rDR_score": 0.86, "VTDR_score": 0.18 },

"evidence_pathway": {

"lesion_counts": { "microaneurysm": 14, "haemorrhage": 9,

"hard_exudate": 3, "soft_exudate": 0 },

"haemorrhages_by_quadrant": { "sup": 4, "inf": 3, "nas": 2, "temp": 0 } },

"reasoner": {

"evidence_grade": 2,

"rules_fired": ["MA present -> at least mild NPDR",

"haemorrhages in 3 quadrants, none >=20 -> 4-2-1 NOT met",

"neovascularisation not observable -> PDR cannot be excluded"],

"unobservable": ["venous_beading", "IRMA", "neovascularisation"],

"max_excludable_grade": 3 },

"verification": { "counterfactual_delta": -2,

"random_region_control_delta": -0.1, "faithful": true },

"agreement":   { "grade_vs_evidence_delta": 0, "disagreement_score": 0.09 },

"decision":    { "action": "ACCEPT", "final_grade": 2, "referable": true }

}

The contrasting case is the one that sells the thesis:

"grade_pathway": { "predicted_grade": 0, "probabilities": [0.91, ...] },

"reasoner":      { "evidence_grade": 2, "rules_fired": ["MA in 2 quadrants"] },

"agreement":     { "grade_vs_evidence_delta": 2, "disagreement_score": 0.83 },

"decision":      { "action": "DEFER", "grade_set": [0, 1, 2],

"reason": "Grader confident normal (p=0.91) but evidence

path found MA and haemorrhages. Confidence

gating would have ACCEPTED this case." }

Figure 1 That second record is a case confidence-based referral accepts and gets wrong, and that this system catches. Experiment G1 exists to find real examples of it in the test set. Go looking for them deliberately — it is the single most persuasive artefact the thesis can produce.

## 7.2 Thesis-level outputs

- Coverage–accuracy curves, five gating arms × three test sets — the headline figure

- Reliability diagrams before and after prior-shift correction, internal versus external

- Results table: QWK, macro-F1, MAE, ECE, rDR AUROC across EyePACS official test, APTOS and Messidor-2, for both training variants

- Per-lesion Dice table and the cross-domain segmentation drop

- Faithfulness table: Δgrade for lesion versus random removal, by severity

- Triage distribution: fraction and accuracy in each action bucket

- Reproducibility bundle: manifests, dataset plan, frozen config and commit hash, checkpoints

# 8. Benefits over existing systems

First, honestly — what this will not beat Raw grading accuracy. A single EfficientNet-B0 at 512 px with no heavy ensemble will land below the best published EyePACS numbers. The thesis must not be framed as an accuracy contribution; that argument would be lost in the viva.

What it does offer:

1.  A referral signal structurally independent of the classifier

The dominant approach defers when the model is uncertain. That has a known failure mode: a miscalibrated network is confidently wrong, and no function of its own logits can detect that, because the error and the confidence come from the same corrupted computation. The evidence pathway here is trained on different supervision — pixel-level lesion annotations from different hospitals in a different country, not image grades — so it can genuinely dissent. Two networks trained on the same labels would agree on the same mistakes; these two need not.

2.  Auditable reasons instead of saliency maps

Most DR interpretability is Grad-CAM heatmaps, which are unfalsifiable — a clinician cannot say a heatmap is wrong. A rule trace stating “nine haemorrhages across three quadrants, 4-2-1 not met” is checkable: they look at the image and either agree with the count or they do not. Falsifiable explanations are a different category of thing.

3.  Explanation faithfulness is measured, not assumed

Almost no DR paper tests whether its explanation is causally connected to its prediction. Experiments E1 and E2 do exactly that, with a control. If it fails, the project will have discovered that its own explanations are decorative — which is itself worth reporting.

4.  The system declares what it cannot see

Existing systems have exactly the same blind spots — no IRMA or venous-beading labels, single-field imaging — and emit a confident grade regardless. This one names them and refuses to exclude what it cannot rule out. In screening, where the cost asymmetry is “missed proliferative DR” versus “one extra human review”, that is the property that actually matters.

5.  Calibration that survives the dataset it was not fitted on

Most papers report internal ECE only. But positive predictive value depends entirely on calibration under deployment prevalence, and grade-0 prevalence moves from roughly 73% to 49% between EyePACS and APTOS. Prior-shift-corrected external calibration is genuinely under-reported and directly clinically load-bearing.

6.  A clean protocol in a field with a leakage problem

Real patient-grouped splits, externals locked and touched once, a pre-registered recipe, and one number reported on the official split for honest comparison. Modest as novelty; substantial as credibility.

## 8.1 Positioning against the closest work

| Prior work | What they did | What this adds |
| --- | --- | --- |
| Leibig et al. 2017 | Uncertainty-based referral in DR | An independent deferral signal, not self-confidence |
| Gulshan 2016; Krause 2018 | High-accuracy grading; label adjudication | Not competing on accuracy — competing on auditability |
| Wei 2020; Sun 2021 | Lesion-aware grading improves accuracy | Lesions used to verify the grade, not to boost it |
| Boreiko et al. 2022 | Generative counterfactual explanations | Counterfactual as a pass/fail faithfulness test feeding a triage decision |

The framing for the abstract Lesion evidence has been used to make DR models more accurate. This work asks whether it can instead be used to decide when to trust them. That is a different question from the one the field has been asking, and it is answerable with Kaggle-available data.

Benefits 1 to 5 are hypotheses until Stage F reports. The thesis must be written so that it holds up if F2 comes out negative — pre-registration is what makes that possible.

# 9. Compute budget and phasing

Kaggle provides 30 GPU-hours per week with a 12-hour session cap. The revised plan costs roughly 100 GPU-hours — three to four weeks of quota, spread across a 16–20 week project. Compute is not the bottleneck; writing and analysis are.

| Stage | Work | GPU-hours |
| --- | --- | --- |
| 0 | 512 px pre-resize cache (CPU only, 6–10 CPU-hours) | 0 |
| 1 | B1 resolution ablation on balanced_1000, one seed | 5 |
| 2 | B2–B4 recipe search on eyepacs_full at 512 px, one seed | 10 |
| 3 | C1 optic-disc / fovea regressor (IDRiD, 516 images) | 1 |
| 4 | C2–C4 evidence U-Net (~840 annotated images), four runs | 4 |
| 5 | Frozen recipe × three seeds × two variants | 12 |
| 6 | B5 eye-pair fusion head | 3 |
| 7 | Stages D, E, F — calibration, faithfulness, triage (inference only) | 5 |
| 8 | Contingency ×2 | ~40 |
|  | Total | ~80–100 |

## 9.1 Phase plan

| Phase | Weeks | Content and exit condition |
| --- | --- | --- |
| 0 | 1 | Protocol and datasets. Exit: all six datasets attached, both verification questions answered in writing |
| 1 | 2 | Build the 512 px cache. Exit: cache published as a Kaggle dataset, A0 logged |
| 2 | 3 | Manifests and patient-grouped splits. Exit: disjointness assertion passes, dataset plan committed |
| 3 | 4–7 | Grading pathway B1–B6. Exit: one recipe chosen on validation; no test set touched |
| 4 | 6–9 | Evidence pathway C1–C4. Exit: C1 meets its target; C2–C4 logged |
| 5 | 10 | THE FREEZE. Pre-registration filled in, committed, supervisor-acknowledged |
| 6 | 11–12 | Final training and the single unblinding. Exit: results on all three test sets |
| 7 | 12–15 | Calibration, faithfulness, triage — D, E, F. Exit: coverage–accuracy curves |
| 8 | 15–17 | Error analysis G1–G3. Exit: figure 1 exists and is a real case |
| 9 | 16–20 | Write-up |

Phase 5 is the point of no return After the freeze commit, the architecture, hyperparameters and decision thresholds do not change. Later changes are allowed but must be recorded as dated deviations in the pre-registration file. Undocumented post-hoc changes are what make results unpublishable.

# 10. Limitations and threats to validity

These belong in the thesis, stated plainly. An examiner who finds a limitation the author did not name is in a much stronger position than one who finds it already discussed.

| Threat | Handling |
| --- | --- |
| Label noise differs between datasets | EyePACS is single-grader; Messidor-2 is three-specialist adjudicated. Part of any gap measures grader disagreement, not generalisation failure. Stated in the discussion. |
| Preprocessing confound | messidor2preprocess may already be contrast-normalised. Verified in Phase 0; if so, matched across sources or reported as a confound. |
| Evidence path may be weak off-domain | C3 measures this directly. If Dice collapses cross-domain, the disagreement signal degrades exactly where it is most needed — a real limitation worth reporting. |
| Small lesion-annotation set | Roughly 840 annotated images in total. Wide confidence intervals expected on Dice; segmentation quality must not be over-claimed. |
| Grade-1 invisibility | Microaneurysms are 10–20 px. If B1 shows near-zero grade-1 recall at all resolutions, the five-class framing is unsupported and the thesis reframes around referable DR (grade ≥ 2). |
| Single-field quadrant approximation | The ETDRS 4-2-1 rule assumes seven fields; this uses one. Declared in the reasoner and in the limitations section. |
| Three seeds is few | Seed spread reported everywhere; no difference claimed that is smaller than seed-to-seed variation. |
| Not a clinical device | Research software. Deployment would require prospective validation and expert oversight. |

Prepared as part of the VERIFY-DR project scaffolding. See the repository documentation set for the full walkthrough (docs/00_START_HERE.md), architecture (docs/03_model_architecture.md), experiment register (docs/04_experiment_register.md) and pre-registration template (preregistration/PREREGISTRATION.md).